## Sheet5
order | time_point | name | sub_name | traits | assigned_to | start | end | days | comments
1 | 0 | UAV 0 | Image |  | Peter | 2025-05-19 | 2025-05-20 | 2
2 | 0 | Stand Count | Stand | establishment | Peter | 2025-05-19 | 2025-05-20 | 2
3 | 1 | Growth 1 | Height | oat_height_t1, pea_height_t1 | Leah, Adrian, Peter | 2025-05-30 | 2025-06-03 | 5
4 | 1 | UAV 1 | UAV |  | Peter | 2025-05-30 | 2025-06-03 | 5
5 | 1 | Research 1 | Image |  | Leah, Adrian | 2025-05-30 | 2025-06-03 | 5
6 | 1 | Calibrator 1 | Biomass | oat_biomass_t1, pea_biomass_t1, weed_biomass_t1 | Leah, Adrian, Peter | 2025-05-30 | 2025-06-03 | 5
7 | 1 | Maintenance 1 | Data, Field |  | Leah, Adrian, Peter | 2025-05-30 | 2025-06-03 | 5
8 | 1.5 | Flowering | Phenology | pea_flowering | Adrian | 2025-06-09 | 2025-07-09 | 31
9 | 1.5 | Heading | Phenology | oat_heading | Adrian | 2025-06-09 | 2025-07-09 | 31
10 | 2 | Growth 2 | Height | oat_height_t2, pea_height_t2 | Leah, Adrian | 2025-06-20 | 2025-06-24 | 5
11 | 2 | UAV 2 | UAV |  | Peter | 2025-06-20 | 2025-06-24 | 5
12 | 2 | Research 2 | PM3D Research |  | Leah, Adrian | 2025-06-20 | 2025-06-24 | 5
13 | 2 | Calibrator 2 | PM3D Calibrator | oat_biomass_t2, pea_biomass_t2, weed_biomass_t2 | Leah, Adrian, Peter | 2025-06-20 | 2025-06-24 | 5
14 | 2 | Maintenance 2 | Data, Field |  | Leah, Adrian, Peter | 2025-06-20 | 2025-06-24 | 5
15 | 2.5 | Maturity | Phenology | maturity | Adrian | 2025-07-09 | 2025-08-01 | 24
16 | 3 | Growth 3 | Height, canopy | oat_height_t3, pea_height_t3 | Leah, Adrian | 2025-07-11 | 2025-07-15 | 5
17 | 3 | UAV 3 | UAV |  | Peter | 2025-07-11 | 2025-07-15 | 5
18 | 3 | Research 3 | Image |  | Leah, Adrian | 2025-07-11 | 2025-07-15 | 5
19 | 3 | Calibrator 3 | Biomass | oat_biomass_t3, pea_biomass_t3, weed_biomass_t3 | Leah, Adrian, Peter | 2025-07-11 | 2025-07-15 | 5
20 | 3 | Maintenance 3 | Data, Field |  | Leah, Adrian, Peter | 2025-07-11 | 2025-07-15 | 5
21 | 4 | UAV 4 | UAV |  | Peter | 2025-08-01 | 2025-08-05 | 5
22 | 4 | Height | Harvest | oat_height_t4, pea_height_t4 | Leah, Adrian | 2025-08-01 | 2025-08-05 | 5
23 | 4 | Lodging | Harvest | lodging | Leah, Adrian | 2025-08-01 | 2025-08-05 | 5
24 | 4 | Grain Harvest | Harvest |  | Peter, Adrian, Leah | 2025-08-04 | 2025-08-08 | 5
25 | 5 | Grain Separation | Harvest | oat_grain_weight, pea_grain_weight | Adrian | 2025-08-12 | 2025-08-16 | 5
26 | 6 | Peter Vacation 1 |  |  |  | 2025-07-02 | 2025-07-06 | 5
27 | 6 | Peter Vacation 2 |  |  |  | 2025-08-16 | 2025-08-24 | 9
28 | 6 | Jean-Luc
29 | 6 | Adrian White
30 | 6 | Leah Treffer

## Sheet1
trial_name | planting_date | t1_expected_date | t2_expected_date | t3_expected_date | t4_expected_date | t1_actual_date | t2_actual_date | t3_actual_date | t4_actual_date
2025_B4I_NY | 2025-04-25 | 2025-05-30 | 2025-06-20 | 2025-07-11 | 2025-08-01
B4I_2025_PM3D_NY | 2025-04-25 | 2025-05-30 | 2025-06-20 | 2025-07-11 | 2025-08-01
Formulas:
t1_expected_date = [planting_date]+35
t2_expected_date = [planting_date]+56
t3_expected_date = [planting_date]+77
t4_expected_date = [planting_date]+98